## DVD106D HIST Log
PIONEER WRITER, Firmware Change History
FW Revision History for PIONEER After Model (Dual Writer Model)
Established on: | [7 empty] | 05/06/2003
Last revised on: | [7 empty] | 05/26/2003
Pioneer corporation, Components Busness Company, Engineering Department 3
Supplier Model Name: |  | DVR-106/A06 (Dual Model)
Bezel Color: |  | Pioneer gray
Style: |  | Dual model (DVD-RW/+RW), without HPJ & volume
Color the word in blue if there is a change against what I reported before.
Change# | Subject | Approval Status | Revision |  | Cut-in date | Pioneer Serial# |  | Remarks
|  |  | F/W | H/W |  | Start | End
000 | Tentative F/W revision | n/a | 0.26A [04/03/2003] | n/a |  | n/a | n/a | Tentative Revision
001 | Tentative F/W revision | n/a | 0.28A [04/11/2003] | n/a |  | n/a | n/a | Tentative Revision
002 | Initial F/W revision | n/a | 1.00 [04/12/2003] | n/a | April, 2003 | n/a | n/a
003 | Refer to FW change history | n/a | 1.01 [04/17/2003] | n/a | April, 2003 | n/a | n/a
004 | Refer to FW change history | n/a | 1.02 [04/24/2003] | n/a | May, 2003 | n/a | n/a
005 | Refer to FW change history | n/a | 1.03 [05/20/2003] | n/a | May, 2003 | n/a | n/a | No QC test is applied for this version.
006 | Refer to FW change history | n/a | 1.04 [05/23/2003] | n/a | May, 2003 | n/a | n/a | No QC test is applied for this version.
007 | Refer to FW change history | n/a | 1.05 [05/26/2003] | n/a | May, 2003 | 000001- |  | QC test is applied

## FW HIST JAPANESE
PIONEER WRITER, Firmware Change History
Firmware Change List (FW変更履歴）
既報告部分に修正点がある場合、青字でハイライトする。
Change No. | Item No. （項目） | Category （変更点カテゴリー） | Problem （問題点） | Cause （原因） | Solution （修正点）
000 | n/a | Tentative revision （暫定版） | n/a | n/a | n/a
001 | 1 | Tentative revision （暫定版） | n/a | n/a | n/a
| 2 | ダウンロード | 仕向け違いのファームをダウンロード直後にハングする場合がある。 通常は 問題ない。 | n/a | 修正する。
| 3 | ストラテジ DVD+RW | n/a | n/a | HS DVD+RW(TDK_____001)ストラテジを追加
| 4 | I/Fコマンド DVD+RW | AppleのMOSS（Writing用のTool）で、ブランクDVD+RWを入れて書き込もうとすると、エラーとなる。(エラー内容としてはWriteCapacityがゼロとなる。) | Read Track/RZone Info Commandを発行したときのDriveの返すDataの違いによる。 | Read Track/RZone Info.で、ブランクDVD+RW挿入時、Free Blocksフィールドで返す値を変更。０を返すことは、仕様として正しいが、このようなアプリがあり、他社ドライブを参考に変更した。
| 5 | RMD更新 DVD-RW | n/a | n/a | DVD-RWでOPC Area Full時、RMDの更新を促すフラグをセット。
| 6 | I/F | 特定のPCにR6がSLAVE時認識されない。 | MASTER/SLAVEシーケンス中（ドライブBSY中）にホストがコマンド発行後、ハードリセットを出してきていた。M/Sシーケンス中はコマンド割り込みは禁止になっているので、ハードリセット時にコマンド割り込みとハードリセット割り込みの両方が立つのだが、コマンド割り込みを無視するようにできていなかった。 | ハードリセット割り込み処理を必ず行うようにした。
| 7 | セットアップ DVD+R/RW | DVD+R/RWでセットアップエラー | DVD+R/RWのセットアップ位置でRF有り無しがまだらになっているDISCがある。 AGCがこの部分でうまく動作できずにエラーとなっていた。 | RF有り無しが切り替わる影響を避けるため、最内周部に退避させてAGCを行う。
| 8 | 同期記録外れ DVD+R | MCC製HS DVD+R 4倍速記録全面記録したDISCを特定の他社製DVDﾌﾟﾚｰﾔで再生確認を行ったところ、必ず立ち上げ出来ないディスクがある。 | ４倍速DVD+Rでリファレンスコードの記録中Wobble PLLがはずれシンクがずれ始める。 その結果追記したコトロールデータをそのプレーヤが読めない | +系のリードイン記録は、リファレンスコード記録後終了し,残りを追記するようにした。
002 | 1 | ストラテジ CD-RW | n/a | n/a | HSのImation(97:24:15)とSKC(97:26:21)の設定を変更。
003 | 1 | サーチ安定性向上 | n/a | n/a | サーチ時の各種制御を細かく見直す。
| 2 | ストラテジ DVD+R | n/a | n/a | DVD+R HS-RICOHのx2.4記録時のβを変更。 DVD+R HS-MAXELLのM-IDを追加。
| 3 | ストラテジ CD-R | n/a | n/a | Fuji Film X48フタロ、NAN-YA,Digital Strageを追加。 SONY X48フタロ、MITSUI X24フタロのストラテジを修正
| 4 | ストラテジ DVD+RW DVD-RW | n/a | n/a | * DVD+RWストラテジ追加＆修正 [MKM_____A02],[SONY____S11],HS DVD+RW追加 NS DVD+RWのストラテジ変更。 * 変更 [MCC 01RW11n9]
| 5 | DVD-R/RW再生性能改善 DVD-R/RW | DVD-R/RWのさらなる再生性能改善。 | 温度環境下でOPUのDefocus特性が悪化し、小さなFocus Balanceずれに対しても大きくError Rateが悪化する。 | DVD+-R/RWのSetup時にFocus Balance調整を追加した。
| 6 | 他社製DVDプレーヤー互換性 DVD+RW | RICOH製DVD+RW 2.4倍速記録全面記録したDISCを特定の他社製DVDﾌﾟﾚｰﾔーで再生確認を行ったところ、この1枚のみ立ち上げ出来ない。 | このDiscをﾌｫｰﾏｯﾄした他社製ﾄﾞﾗｲﾌﾞとR6ﾄﾞﾗｲﾌﾞのﾘﾝｸ位置がずれている(1Wobble弱)事が原因と思われます。 | DVD+RWの他社ドライブ互換性維持のためDCB、Control Data、LBA 0 から記録するときにヘッダブロックを 4 ECC 付加する。
| 7 | DC-EraseでF-OUT CD-RW | CD-RWのDC Erase時にF-OUT CD-RWでOPCをやったあと、DC Eraseを行うと、DC Erase終了時にPauseになったときにFocus外れがおこる。 | RWでOPC時にALPCリードパワー設定をフロントモニタからのフィードバックで可変させる処理で余計な操作をしていた。 | 修正する。
| 8 | ストラテジ DVD-R DVD+R | n/a | n/a | * DVD-R ストラテジ変更（修正） PRINCO 1X PRINCO2 1X VIVASTAR 1X OPTODISCK001 1X LD 1X Lead Data 1X Auvistar 1X CMC00RG200 1X RITEKG02 1X RITEKG03 1X CMC MAG. 1X LGE02 1X PRODISCG02 1X PRODISCG02 2X CMC MAG.メディア1X CMC MAG.メディアの2X MXL RG01メディアの2X * DVD+Rストラテジ変更 MAXELL__001 2.4X,4X
004 | 1 | Radius NS DVD-RW DVD-RW | RADIUS－ＲＷ記録できない。 | アンリーダブルエンボスからの記録のためのサーチでトラッキング外れてしまう。 アンリーダブルエンボスのＬＰＰが読み辛い。 | リーダブルエンボス部からアンリーダブルエンボス部へジャンプしてSerach&Recする場合、リーダブルエンボスの最外周部までジャンプしてトレースする。 Unreadable emboss後の追記でリトライでの記録開始までのトレース中、LPPスライスレベルを下げる。
| 2 | DVD+R他社互換性 DVD+R | 他社製ドライブで、DLAを使って書いたDVD+Rが、R6では空ディスクと認識され、かつDLAによる追記もできない。 | 他社製ドライブでDVD+RディスクのDLAフォーマットを行った場合、SDCBを書かずに書き始める(規格外の書き方)ため。 | SDCBを書かずに書き始めたDVD+RもIncomplete Discとして認識するように変更。
| 3 | I/F コマンド DVD-RW | DVD-RW のフォーマットで OPC が終わった時に、一瞬だけ Test Unit Ready がGood になるタイミングがあった。(本来は、2/4/4 Format In Progress) | n/a | 修正。
| 4 | ストラテジ CD-R | n/a | n/a | * CD-Rストラテジ微調 FujiFilm ｼｱﾆﾝ 16X maxell new 三菱ｽｰﾊﾟｰｱｿﾞ 8X MITSUI 63 12X TDK X48ﾌﾀﾛ 12X TDK 80new SONY X32ｼｱﾆﾝ PRODISC RITEK Gtype 12X RITEK Rtype 16X SKC ｼｱﾆﾝ Acer ﾌﾀﾛ 8X Gigastorage ﾌﾀﾛ 4X Gigastorage ｼｱﾆﾝ80 4X 8X 12X LeadData X32ﾌﾀﾛ 4X 8X LeadData X32ｼｱﾆﾝ 4X 16X Princo MBI 80 8X MBI 90 12X 16X * CD-Rストラテジ再設定 MITSUI X24ﾌﾀﾛ SONY X48ﾌﾀﾛ
| 5 | ストラテジ CD-RW | n/a | n/a | LS CD-RWのストラテジ修正
| 6 | ストラテジ DVD-R/+R | n/a | n/a | * DVD-Rストラテジ修正 MEI_00V001の2Xストラテジ修正 * DVD+Rストラテジ変更 RICOHJPNR00の2Xストラテジを更新 CMC_MAG_R01の2X個別ストラテジ設定 PRODISC_R01の2X個別ストラテジ設定 CMC_MAG_F01の4X個別ストラテジ設定
005 | 1 | ランダムアクセス動作の安定化 CD、DVD | CD/DVD Random Access性能のばらつきが大きい。DVD-DualでRandom Access中にFocus外れ発生。 | Traverseの速度制御NGの判定部分に不具合があり、容易にNGルーチンに入る。また、NGルーチンに入ると処理に時間がかかる。さらにDual LayerではNG検出できないこともありFocus外れも発生している。 | Traverse中の速度制御NGをTrack横切り速度から検出するように変更。Stepper割り込みが発生した直後、現在速度を読み取り、その値が目標速度に対しある値となるとNGと判断し、中点制御に移行する。
| 2 | シークでT-ALM発生 CD-R/RW未記録部 | CD-R/RWの未記録部のSeekでT-ALMが発生する。 | Radial Contrast信号をPeak Detect Blockに入れMIRR検波を行っているがRadial Constrast信号はMain信号和のみでは振幅が安定しない。 | Radial Constrast信号はMain信号和のみでは振幅が安定しないので、Main信号和－２KｘSub信号和のRadial信号を使用する。
| 3 | APPLI OFFモードでSDCB書き込み抜け | 特定のPCにR6がSLAVE時認識されない。USB－ATA変換ボード使用で記録中にエラーが発生する。 | APPLI OFF（非定義）時、SDCB（DVD+R)書き込みルーチンのコール抜けがあった。 | これを修正。
| 4 | チルトラジアル初期値出し | 記録済みDVD＋RW／－RWセットアップで、エラーディスクとなってしまう。 | TMチルト、ディスク反り、書き込みRFが全て悪い場合RDMやFDCBのリードができなくなる。立ち上げ時に球面収差の調整後、ラジアルの初期値センター出しを行っていない。 | ラジアルの初期値センター出しを行う。
| 5 | ストラテジ DVD-R | 松下４XDVD-Rメディア（MEI 00V002)のマニュファクチャIDとストラテジの修正。 MCI４XDVD-Rメディア（MCI4XG01)のストラテジ修正。 ４X DVD-Rメディアの追加（SONY、RITEK、GSC、LEADDATA、Prodisc、SKC）
| 6 | IFコマンド | Read DVD StructureのRMD（Format 0Dｈ）転送で、８バイト少ない場合がある。 | 本来、最大でデータ32768バイトとヘッダー8バイトがあるが、指定されたLengthを32768で制御してしまっていて大きなLengthを指定されたとき8バイト少なくなっていた。 | Lengthを32768＋8で制限するように変更する。
| 7 | IFコマンド | RoxioのECDC6にて＋Rでフリーズ発生。 | ECDC6はFaｈのPacketCommandを発生し、R6はこのコマンドをEE系によるエンコード／でコードチェック用のテストコマンドと認識され、ホストからのデータを待ったままになっている。 | このテストコマンドは現在使われていないので、INVALID COMMANDとする。
| 8 | IFコマンド | NeroでDVD＋RWのB.G.F後うまく動作しない。 | DVD+RWのB.G.Fは初期化フォーマットが終ってから約１０秒後に開始している。その間にDisc InformationのBG Format StatusをO1ｂ（BG Format is not runnig)になっているため。 | その間、BG Format Statusを１０ｂ（BG Format is in progress) にするよう仕様変更。
| 9 | DVD－Dual ランダムアクセス | ライン検査にてDVD-Dual Random AccessでT-ALM、FCS外れが発生 | MIRRが長期間欠落し、サーチ終了後にT-Closeできない事があった。 | Dual時のMIRR欠落を削減するために、RF Boost Tableを最適化した。
| 10 | CD-DAコピーで音とび CD-R | CD-R CD-DAのCD-RWへのCopyで、音飛び発生。 | Copy元CD-Rのエラーレートが悪く、訂正不能による前値ホールドが発生。 | CD-R用のFR Boost設定が最適でなくエラーレートを悪化させていたのでこれを最適化した。
| 11 | DVD-Dual Setup NG | Setup Time Outが発生 | OPUのばらつきによる球面収差ズレでFbal調整終了までのDPD信号品質が悪化。その結果、T-ALMを語検出してMedia Changeを繰り返しSetup NGとなる。 | 記録済みメディア CLVのみT-ALM感度を上げていたが、これを他のメディアと同じ感度に設定した。
| 12 | HS CD-RW他社互換性 | R6と他社ライターで交互にWrite／Eraseを繰り返すとディスクが認識不能となる。（MCC HS CD-RW） | 高温下でのWrite Powerが高めに設定されており、DOW特性が悪化していた。 | MCCのHS CD-RWを個別ストラテジとして対応した。
006 | 1 | プレアビ改善（フインガープリント） DVD+RW | DVD+RWの７５um フインガープリントで3－11－05エラーの発生 | DVD+RWのプレアビディスクをリードした際に十分なリトライを実行しないまま、タイムアウトエラーになってしまうことがある。 | リトライ発生時のバッファリング開始アドレスの修正も含め、最適なリトライ動作を実行するように修正する。
| 2 | スタートアップ タイムオーバー DVD-Dual | Dual Start Up Time Over | DualのSetupでLayer１へのFocus Jumpに失敗したとき、SetupのリトライルーチンでT-Openしながらｃ－ｓｄｒをCheckし続ける箇所があったため。 | T-OpenしながらのFocus Jumpで失敗した場合、Focus In後T-closeできるように変更。
| 3 | PCA Error DVD-R | OPTODISC001 DVD-Rで、PCA Error（3－73－3）となる。 | PCA for disc manufacture areaの先頭付近に記録があり、本来Virgin Discであるはずのディスクに対してこのアドレスをリトライしていた。その結果、OPC end seek エラーとなり、Send OPC コマンドに対し、3－73－3エラーが返っている。 | SYRECDコマンドの応答を待ちながらトレースを行っている際の、異常なアドレス検出処理に問題あり。PCA fordisc manufacture areaのアドレスがDSPから返る場合はVirgin Discとする。
| 4 | ストラテジ DVD＋R |  | NS及びHS DVD＋Rのデフォルトストラテジのターゲットβに間違いあり。 | RITEC＿R02のストラテジ追加。 NS/HS DVD+Rのデフォルトストラテジのターゲットβを修正。
| 5 | ストラテジ CD-R |  |  | Fuji X32フタロストラテジの追加。 三菱スーパーアゾHG １６X ストラテジ更新。 SKC X52フタロストラテジの追加。 ACERフタロストラテジ変更。 Gigastorageフタロストラテジ変更。
007 | 1 | DRT-DM -5℃で過検出 | DRT-DMの-５℃環境下試験で、検査NG（Error Rate悪多発）。本来ディフェクティブブロックでないものも、ディフェクティブと判断してしまう。 | Radial TiltのOffsetがSearch後必ず０になってしまうのが原因。 DRT-DMでは、Read時のError Rate測定安定性を向上させる為、Read時でもSearch＆Recを使用しSearchしてるが、Writeが実行されなていない状態で、この機能を使うと、Tilt Profileが測定されていないので、Search中のTilt Hold時に必ず０が設定されていた。 | Profileが実行されていない場合は、Search＆Rec時のHoldで０を設定するのではなく、Search前の前置をHoldする。
| 2 | CD-RWセットアップできず | ＤＶＤ記録後に、ＣＤ－ＲＷのセットアップができない。 | ＡＴＩＰが読めていない。 これは、ＷＤＰＬＬの設定が、もともとは、周波数検出＋周波数引き込みであったものが、ＤＶＤに記録後には、周波数引き込みのみになっていることが影響していた。 | 今までMainの頭でのみ設定していた517hの値をset_default_value()内でもやる。 同じ値を書くだけなので動作上変化なし。
| 3 | 8cmDVD+RWの外周FDCB書き込み |  |  | DVD+RW で外周の FDCB を記録するアドレスが 12cm ディスクの固定値になっているので ADIP に書かれている最後のアドレスから計算するように変更。

## FW HIST ENGLISH
PIONEER WRITER, Firmware Change History
Firmware Important Change List
Color the word in blue if there is a change against what I reported before.
Change No. | Item No. | Category | Problem | Cause | Solution
000 | n/a | Tentative revision | n/a | n/a | n/a
001 | 1 | Tentative revision | n/a | n/a | n/a
| 2 | Download | Sometimes drive is hung up just after when the different customer code is downloaded on it. There is no problem as long as FW downloading for the same customer. | n/a | Fixed
| 3 | Strategy DVD+RW | n/a | n/a | HS DVD+RW(TDK_____001)'s strategy is added.
| 4 | I/F command DVD+RW | In case of Apple MOSS(Writing tool), an error is occurred when the drive reads the inserted blank DVD+RW. (Error: WriteCapacity = 0) | Depending on the returned data according to Read Track/RZone Info command. | Returning "0" doesn't violate the specification. The competitor drive returns unique value according to Read Track/RZone Info when the blank DVD+RW is inserted. To avoid the error, we follow their way.
| 5 | RMD renewal DVD-RW | n/a | n/a | Renewal flag is defined when the OPC Area is full on the inserted DVD-RW media.
| 6 | I/F | The drive(R6) isn't recognized when it is on Secondary/Slave in two connected drive. | Host issues Hard RESET just after a command even though the drive insists BUSY status in MASTER/SLAVE sequence. Both hard reset interruption and command interruption is generated at the RESET. But the drive can't ignore the command interruption then it isn't recognized by BIOS. | An algorithm inside is changed to avoid the problem. The Hard Reset process must be done even during the Master/Slave sequence without command interruption when it is required.
| 7 | Setup DVD+R/RW | An Setup error is occurred with DVD+R/RW media. | The DVD+R/RW media has the area where is recorded alternately very short period then the drive doesn't settle the RF AGC control and does make the error. | To prevent the influence the recorded existence alternately in a very short period, the drive does the AGC control at the most inner area on the disc.
| 8 | Synchronization DVD+R | Some competitor DVD player never recognize a MCC HS DVD+R media which is recorded full area in 4x by the drive(R6). | Wobble PLL is run off the sync while the drive is recording a reference code by 4x on the DVD+R. As the result of this, the player doesn't keep recording the rest of control data in sync. | In case of "+" type media recording, the drive once finishes the recording until the reference code then starts again the rest of recording in order to prevent out of sync problem.
002 | 1 | Strategy CD-RW | n/a | n/a | HS, Imation(97:24:15) and SKC(97:26:21) is modified.
003 | 1 | Improving search performance | n/a | n/a | Several processes in search sequence are tuned up.
| 2 | Strategy DVD+R | n/a | n/a | DVD+R HS-RICOH (x2.4)s β(Beta) is changed. DVD+R HS-MAXELL's MID is listed.
| 3 | Strategy CD-R | n/a | n/a | Fuji Film X48 Phthalo, NAN-YA, and Digital Storage are added. SONY X48 Phthalo and MITSUI X24 Phthalo is modified.
| 4 | Strategy DVD+RW DVD-RW | n/a | n/a | * DVD+RW's strategy is added and modified. [MKM_____A02], [SONY____S11]; HS DVD+RW is added. NS DVD+RW's strategy are changed. * Changed. [MCC 01RW11n9]
| 5 | Improving playability performance DVD-R/RW | To improving DVD-R/RW playability performance. | The error rate get to be been worse in spite of the slight focus balance off. Because the defocus performance of OPU is get to be worse by the temperature rise and fall. | The focus balance adjustment step is added when the inserted media is either DVD-R/RW or DVD+R/RW.
| 6 | Media playback compatibility DVD+RW | One RICOH DVD+RW media recorded fully by 2.4x isn't recognized by some competitor DVD player. | There is about one wobble difference at the link position between a competitor and R6. The media is formatted by the competitor but recorded by 2.4x by R6. | To make media playback compatibility good, 4 ECC header block is padded no matter when new data is recorded from DCB, Control, or LBA 0.
| 7 | Focusing out in DC erase CD-RW | Focusing out is occurred while the drive do DC Erase on CD-RW media. After OPC completed, a focusing out is happened at Pause mode just after finishing DC Erasing.. | Unnecessarily process is existed while the drive controls ALPC read power setting through the feedback from a front monitor diode at OPC operation on CD-RW media. | Fixed
| 8 | Strategy DVD-R DVD+R | n/a | n/a | * DVD-R's strategy is fined. PRINCO (1X) PRINCO2 (1X) VIVASTAR (1X) OPTODISCK001 (1X) LD (1X) Lead Data (1X) Auvistar (1X) CMC00RG200 (1X) RITEKG02 (1X) RITEKG03 (1X) CMC MAG. (1X) LGE02 (1X) PRODISCG02 (1X) PRODISCG02 (2X) CMC MAG. (1X) CMC MAG. (2X) MXL RG01 (2X) * DVD+R's strategy is changed. MAXELL__001(2.4X,4X)
004 | 1 | Servo (Tracking) DVD-RW (Radius NS DVD-RW) | The drive doesn't record on Radius DVD-RW. | The tacking servo is been off as the recording is started from unreadable-emboss. Because it is hard to read unreadable-emboss LPP for R6. | The drive traces the track to the target unreadable-emboss address from the most outside of readable-emboss area when the Search&Rec have to be done with the direct jump to unreadable-emboss to readable-emboss. The LPP slice level is got to be lower during the trace.
| 2 | DVD+R compatibility DVD+R | The drive(R6) recognizes it as blank and can't record under DLA, but the media which was recorded by DLA on a competitor's drive. | The competitor drive doesn't record SDCB first preceding the data recording. | The drive recognizes DVD+R as Incomplete Disc even though the media is recorded without SDCB.
| 3 | I/F command DVD-RW | There is a moment that the drive returns GOOD against Test Unit Ready just after OPC operation is completed during DVD-RW formatting. (naturally 2/4/4; Format In Progress) | n/a | Fixed
| 4 | Strategy CD-R | n/a | n/a | * CD-R's strategy is fined. Fuji Film Cyanine (16X) Maxell new MCC Supper-Azo (8X) MITSUI 63 (12X) TDK X48 Phthalo (12X) TDK 80new SONY X32 Cyanine PRODISC RITEK Gtype (12X) RITEK Rtype (16X) SKC Cyanine Acer Phthalo (8X) Gigastorage Phthalo (4X) Gigastorage Cyanine80 (4X 8X 12X) LeadData X32 Phthalo (4X 8X) LeadData X32 Cyanine (4X 16X) Princo MBI 80 (8X) MBI 90 (12X 16X) * CD-R's strategy is changed. MITSUI X24 Phthalo SONY X48 Phthalo
| 5 | Strategy CD-RW | n/a | n/a | LS CD-RW's strategy is modified.
| 6 | Strategy DVD-R/+R | n/a | n/a | * DVD-R's strategy is modified. MEI_00V001 (2X) * DVD+R's strategy is modified or added RICOHJPNR00 (2X) CMC_MAG_R01 (2X) PRODISC_R01 (2X) CMC_MAG_F01 (4X)
005 | 1 | Random access on CD, DVD | The range of Random access data becomes wider than standard distribution. Focus error occurs at random access operation at DVD dual disc. | Miss program takes place at part of speed control NG detect for traverse and easily enters into the NG routine. Once enters NG routine, operation speed becomes slow and Focus error occurs at Dual disc. | Change speed control NG detection with track count. Read current speed when Stepper interruption occurs then compare it with center speed in order to detect NG or GOOD.
| 2 | Tracking ALM at blank CD,DVD | Tracking ALM occurs at seek operation at blank area of CD-R/RW disc. | MIRR detection is done in Peak detection block with radial contrast signal. The amplitude of radial contrast becomes unstable if it is make by Main signal only. | To make radial contrast signal stable, use Main signal - 2KxSub signal for radial signal.
| 3 | SDCB not written at APPLI OFF mode | The writer is not recognized as SLAVE connection. An writer error occurs when ATA-USB board is used. | A call program at write routine for SDCB (DVD+R) is not implicated when APPLI OF mode. | Fixed this bug.
| 4 | Tilt radial initial value | An error disc is made at set-up operation of pre-recorded DVD+RW/-RW disc. | With combination of bad TM tilt, Disc vending, and quality of RF signal, RDM and FDCB signal are not read. An initial center value of radial is not set when set-up operation after LCD tilt adjustment. | Execute setting of initial radial center value.
| 5 | Strategy DVD-R | Changed manufacture ID and strategy of Panasonic DVD-R 4X media (MEI 00V002). Change write strategy for MCI4XG01. Add support media of 4X DVD-R. (SONY, Ritec, GSC, Prodisc, Readata, SKC)
| 6 | IF command | 8 bytes less data transfer is occurred at RDM transfer (Format 0Dh) at Read DVD Structure command. | Max. data size is 32768 bytes and header is 8 bytes. At anytime, 32768 byte is transferred without the header bytes. | Length is controlled as 32768+8 Bytes.
| 7 | IF command | PC hangs with +R media with Roxio ECDC6. | The drive waits data from the host by recognition of test command for code check when ECDC6 issues Fah Packet Command. | Set this command as INVALID COMMAND since it is not used now.
| 8 | IF command | Does not work well after DVD+RW B.G.F. with Nero. | BG Format Status of Disc Information becomes 01b(BG format is not running) while initialization and B.G.F. operation. | Change BG Format status with 10b(BG Format is in progress)
| 9 | DVD-Dual Random Access | T-ALM and FCS error happen at random access at DVD-Dual disc. | Doesn't work T- Close after search operation by lack of MIRR signal. | Optimized RF Boost Table in order to fix lack of MIRR signal at Dual disc.
| 10 | Audio interruption at CD-R | Audio Sound interruption (skip) occurs when copy from CD-DA CD-R disc to CD-RW. | Pre-signal hold function activates by un-correction caused by bad error rate of original CD-R disc. | Optimized RF Boost Table in order to improve error rate at CD-R disc.
| 11 | Set Up NG DVD-Dual | Set up time out occurs | T-ALM is miss detected by bad quality of DPD signal then the writer tries Media Change until Setup-NG. | T-ALM detection level for recorded media at CLV read is higher than other media, so, it is changed the same level as other media.
| 12 | HS CD-RW | The disc is not recognized if the disc is Write/erase between Pioneer R6 and other brand writer alternatively. | DOW level becomes worse by high write power in high temp. | Individual write strategy is applied for MCC HS CD-RW media.
006 | 1 | Improve Playability(Fingar print) DVD+RW | 3-11-05 error occurs at 75um finger print DVD-RW disc. | Time out error occurs without enough number of retry operation when DVD+RW playability disc is played. | Improved as execute optimal re-try operation with correction of buffering start address when retry occurs.
| 2 | Start-up time over DVD-Dual | Start up time over occurs at DVD Dual disc | By a bug of program, the drive checks c-sdr with T-open condition at setup retry routine in case it fails Focus Jump to Layer 1 . | Change as T-Close after Focus in when fails Focus Jump with T-open condition.
| 3 | PCA Error DVD-R | PCA Error (3-73-3) occurs on OPTODISC001 DVD-R disc | The disc has recorded area at the beginning of PCA for disc manufacture area. It retries this area then OPC end seek error occurs and 3-73-3 error returns against Send OPC command. | Abnormal address detection routine exist in trace mode while waiting response of SYRECD command . The disc is recognized as virgin disc in case address of PCA for disc manufacture area is returned by DSP.
| 4 | Strategy DVD+R |  | Target beta of default strategy for NS/HS DVD+R disc are incorrect. | Add strategy of RITEC_R02. Fix target beta of default strategy
| 5 | Strategy CD-R |  |  | Add strategy of Fuji X32 phtalo. Modify strategy Mitsubishi Super Azo HG 16X. Add strategy of SKC X52 phtalo. Add strategy of ACER phtalo.
007 | 1 | DRT-DM (Defect Management) over detection in low temp. | Detect as defect area even good area by bad error rate in low temp. (-5 C Deg.) | Offset of Radial tilt becomes 0 after search operation. At DRT-DM, Search & Rec is used in order to make error rate at read mode stable. Without write operation, 0 is always set as tilt offset since tilt profile is not checked. | In case Tilt profile is not executed, pre-data is held just before search operation at Search & Rec instead of 0 setting.
| 2 | Set Up NG CD-RW | CD-RW set up cannot be done after DVD writing. | Cannot read ATIP signal. Basically, setting of WDPLL are done by both frequency detection and frequency capture, but, only frequency capture is activated. | Set 517h done at the top of Mail is executed in set_default_value().
| 3 | FDCB no write 8cmDVD+RW |  |  | The address of FDCB is set for 12cm disc by mistake. It is changed to calculate by using the last address written in ADIP.